## Blockers
ID | Title | Severity | Status | Resolution / Rationale | Target
BLK-001 | OVMS Empty Config | P0 | CLOSED | scripts/init_models.sh generates model_config.json. | MVP_Cloud
BLK-002 | No Local GenAI | P0 | CLOSED | OVMS 2025.4 native GenAI support enabled. | MVP_Cloud
BLK-010 | A2A v0.3 Compliance | P0 | CLOSED | main.py refactored to use a2a-python SDK. | MVP_Cloud
BLK-016 | Multi-Tenant Storage | P0 | CLOSED | Ceph S3 Buckets created via setup_tenants.sh. | MVP_Cloud
BLK-017 | OpenBao Dev Mode | P0 | CLOSED | Forced Root Token -dev-root-token-id=root. | MVP_Cloud
BLK-023 | Etcd Security | P0 | CLOSED | Upgraded to v3.5.17. | MVP_Cloud
BLK-027 | MinIO AGPL Risk | P0 | CLOSED | Replaced with Ceph (LGPL/Apache). | MVP_Cloud
BLK-028 | Argo K8s Dependency | P0 | CLOSED | Replaced with AsyncDAGEngine (Python). | MVP_Cloud
BLK-029 | Missing Orchestrator | P0 | CLOSED | Implemented src/orchestrator/engine.py. | MVP_Cloud
BLK-030 | AVX-512 Crash Risk | P0 | CLOSED | check_avx512.sh guardrail added. | MVP_Cloud
BLK-031 | Ceph CORS Issue | P0 | CLOSED | s3cmd setcors added to entrypoint. | MVP_Cloud
BLK-034 | Phantom DB Dependency | P0 | CLOSED | Removed asyncpg; Switched to etcd3 for State. | MVP_Cloud
BLK-035 | Protocol Mismatch | P0 | CLOSED | Changed Proxy Target to HTTP/REST (Port 9001). | MVP_Cloud
BLK-036 | Data Persistence | P0 | CLOSED | Added Docker Volumes for Ceph (Data+Config) & Etcd. | MVP_Cloud
BLK-037 | Container Permissions | P0 | CLOSED | Added scripts/fix_perms.sh to pre-boot sequence. | MVP_Cloud
BLK-038 | Dependency Ambiguity | P0 | CLOSED | Pinned python-etcd3 & added smoke test. | MVP_Cloud

## Actions
ID | Action | Owner | Deps | Deadline | Exit Criteria
ACT-100 | Create scripts/check_avx512.sh | Platform | None | T-0 | Script returns 0 on AVX-512 hosts; warns on others.
ACT-101 | Update requirements.txt | Platform | None | T-0 | a2a-python>=0.3, python-etcd3, aioboto3 (Async S3).
ACT-102 | Create src/orchestrator/engine.py | Platform | ACT-101 | T-0 | Engine uses etcd3 for locking; aioboto3 for S3.
ACT-103 | Refactor workflows/main.py | Protocol | ACT-101 | T-0 | Endpoints replaced with A2AFastAPI router.
ACT-104 | Update docker-compose.yml | DevOps | None | T-0 | Map Ceph (Data+Conf) / Etcd Volumes; Set Vault Root Token; Healthchecks added; restart: unless-stopped.
ACT-105 | Create scripts/init_models.sh | Platform | ACT-104 | T-1 | TinyLlama GGUF + model_config.json generated.
ACT-106 | Create scripts/setup_tenants.sh | Security | ACT-104 | T-1 | User tenant-a created in Ceph RGW.
ACT-107 | Configure budget-proxy/routes.yaml | Platform | None | T-1 | Route tinyllama to http://ovms:9001 (REST).
ACT-108 | Implement MCP Bridge | Integration | ACT-102 | T-2 | engine.py calls MCP tools dynamically.
ACT-109 | Create scripts/fix_perms.sh | DevOps | ACT-104 | T-0 | Script chowns ./data/ directories to container UIDs.
ACT-110 | Update Deployment_Order logic | DevOps | ACT-105 | T-0 | setup_tenants.sh waits for ceph healthcheck. engine.py waits for etcd healthcheck.
ACT-111 | Verify Package Imports | Platform | ACT-101 | T-0 | CI/Script runs python -c "import etcd3; ..." to catch naming ambiguity.

## Code_Gaps
ID | File Path | Change Specification
CG-101 | requirements.txt | Remove asyncpg. Add python-etcd3==0.12.0 (State), aioboto3==11.3.0 (S3), boto3, tenacity==8.2.3, grpcio==1.60.0 (Pinned). Smoke test: python -c "import etcd3; import aioboto3; import grpc".
CG-102 | src/orchestrator/engine.py | Use etcd3 client for Distributed Locking. Use aioboto3 for Artifact persistence.
CG-103 | workflows/main.py | Remove @app.post("/task"). Add app.include_router(A2AFastAPI(agent).router).
CG-104 | docker-compose.yml | Ceph: Vols ./data/ceph:/var/lib/ceph, ./data/ceph_conf:/etc/ceph. Etcd: Vol ./data/etcd:/etcd-data, Env ETCD_DATA_DIR=/etcd-data, Command /usr/local/bin/etcd --data-dir=/etcd-data. OpenBao: Command server -dev -dev-root-token-id=root.
CG-105 | docker-compose.yml | OVMS: Expose Port 9001 (REST). Env ONEDNN_MAX_CPU_ISA=AVX512_CORE. CMD: --config_path /models/model_config.json. Healthchecks on etcd (etcdctl endpoint health), ceph (curl -f http://localhost:8000), ovms (curl -f http://localhost:9001/v2/health/live). restart: unless-stopped for all.
CG-106 | config/budget-proxy.yaml | Add routing rule: model: tinyllama -> target: http://ovms:9001.
CG-107 | scripts/check_avx512.sh | Enforce: If AVX-512 not found, exit 1 (Fail Fast). User must override with FORCE_NO_AVX=1.
CG-108 | scripts/fix_perms.sh | Create script to chown -R 167:167 ./data/ceph and chown -R 1001:1001 ./data/etcd before boot.

## Deployment_Order
Phase | Step | Service/Script | Command | Validation
0 | 1 | Hardware Check | ./scripts/check_avx512.sh | Output: "HARDWARE PASS" (or explicit override)
0 | 2 | Permission Fix | ./scripts/fix_perms.sh | ./data owned by correct UIDs
0 | 3 | Dependency Install | pip install -r requirements.txt | python -c "import etcd3; import grpc" passes
0 | 4 | Model Hydration | ./scripts/init_models.sh | model_config.json & GGUF exist
1 | 5 | Infrastructure Boot | docker compose up -d ceph-demo etcd openbao | Wait for docker compose ps -> healthy
1 | 6 | Security Init | ./scripts/setup_tenants.sh | s3cmd ls shows buckets (Retries until success)
2 | 7 | Full Stack Boot | docker compose up -d | All containers up & healthy
3 | 8 | Health Check | curl localhost:8080/health | {"status": "healthy"}
4 | 9 | E2E Test | Chat UI -> "Why is sky blue?" | Response from Local LLM via REST

## SDK_Requirements
Package | Version | License | Foundation | Status
python-etcd3 | 0.12.0 | Apache-2.0 | Independent | APPROVED
aioboto3 | 11.3.0 | Apache-2.0 | Independent | APPROVED
a2a-python | 0.3.0 | Apache-2.0 | Linux Foundation | APPROVED
openvino-genai | 2025.4.0 | Apache-2.0 | Intel OSS | APPROVED
optimum-intel | 1.22.0 | Apache-2.0 | Intel OSS | APPROVED
fastapi | 0.115.6 | MIT | Independent | APPROVED
grpcio | 1.60.0 | Apache-2.0 | CNCF | APPROVED
pydantic | 2.10.5 | MIT | Independent | APPROVED
tenacity | 8.2.3 | Apache-2.0 | Independent | APPROVED
boto3 | 1.35.0 | Apache-2.0 | Independent | APPROVED
asyncpg | REMOVED | N/A | N/A | REMOVED

## Architecture_Gaps
ID | Gap | Solution in v14.1 (Cloud) | Solution in v15.0 (Bare Metal)
GAP-012 | Storage Isolation | Logical: Ceph S3 Policy + Tenant Buckets | Physical: Rook-Ceph Block Devices
GAP-025 | Orchestration | Lightweight: AsyncDAGEngine (Etcd State) | Heavy: Argo Workflows (K8s)
GAP-030 | Protocol Mismatch | Adapter: Budget Proxy (REST -> REST) | Native: Mesh gRPC (Envoy/Cilium)
GAP-031 | Secret bootstrapping | Static: Root Token in Compose | Dynamic: Vault Agent Injector

## Validation_Gates
ID | Gate Name | Method | Pass Criteria
VG-101 | Hardware Compatibility | Run check_avx512.sh | Exit Code 0
VG-102 | Protocol Compliance | curl /tasks/send | JSON-RPC 2.0 Response (ID; Result)
VG-103 | Local Intelligence | Chat UI Prompt | Response generated without WAN traffic
VG-104 | Data Sovereignty | Check Ceph Bucket | JSON Artifact found in tenant-a/
VG-105 | Security | Check OpenBao | Secrets retrieved via Agent
VG-106 | Resilience (Restart) | docker compose restart | Etcd Lock holds; Ceph Data/Keys persist; No Permission Denied errors.
VG-107 | Resilience (Recreate) | docker compose down && docker compose up -d | Data persists (Volume check); Identity stable.
VG-108 | Dependency Smoke | python -c "import ..." | Exit Code 0 (No ImportError).
VG-109 | AVX-512 Guard | check_avx512.sh | Exits 1 on non-compatible hardware (Fail Safe).